## Sheet1
Weeks Task : Person | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28
A: Rasel | Week 1: Overall Planing
B: Nafiul | Week 2: Architecture Design
C: Sadman | Week 2: Product backlog
A: Rasel | Week 4: Analysis
B: Nafiul | Week 4: Design
C: Sadman | Week 6: Development
A: Rasel | Week 8: Testing
B: Nafiul | Week 9: Analysis
C: Sadman | Week 9: Design
A: Rasel | Week 11: Development
B: Nafiul | Week 13: Testing
C: Sadman | Week 14: Analysis
A: Rasel | Week 14: Design
B: Nafiul | Week 16: Development
C: Sadman | Week 18: Testing
A: Rasel | Week 19: Analysis
B: Nafiul | Week 19: Design
C: Sadman | Week 21: Development
A: Rasel | Week 23: System Testing
B: Nafiul | Week 24: Intregration
C: Sadman | bar: Week 26 to Week 28
Rasel | Week 27: Documentation
[6 empty] | Development Phase (In-Game) | [9 empty] | Development Team-
| Activity Key- | [9 empty] | Post-Game
[6 empty] | D : | Sprint Backlog List | [8 empty] | Rasel
| Pre-Game | [9 empty] | Q : | System Intregation |  |  |  | Nafiul
[7 empty] | Module-1 |  |  |  | R : | System Testing |  |  |  | Sadman
| A : | Overall Planning |  |  |  | E : | Analysis |  |  |  | S : | Documentation
| B : | High-level architecture design |  |  |  | F : | Design |  |  |  | T : | Final Release
| C : | Update Product Backlog |  |  |  | G : | Development
[6 empty] | H : | Testing
Module-2
[6 empty] | I : | Analysis
[6 empty] | J : | Design
[6 empty] | K : | Development
[6 empty] | L : | Testing
Module-3
[6 empty] | M : | Analysis
[6 empty] | N : | Design
[6 empty] | O : | Development
[6 empty] | P : | Testing

## Sheet2
Weeks | Week-1 |  |  |  |  | Week-2 |  |  |  |  | Week-3 |  |  |  |  | Week-4 |  |  |  |  | Week-5 |  |  |  |  | Week-6 |  |  |  |  | Week-7 |  |  |  |  | Week-8 |  |  |  |  | Week-9 |  |  |  |  | Week-10 |  |  |  |  | Week-11 |  |  |  |  | Week-12 |  |  |  |  | Week-13 |  |  |  |  | Week-14 |  |  |  |  | Week-15 |  |  |  |  | Week-16 |  |  |  |  | Week-17 |  |  |  |  | Week-18 |  |  |  |  | Week-19 |  |  |  |  | Week-20 |  |  |  |  | Week-21 |  |  |  |  | Week-22 |  |  |  |  | Week-23 |  |  |  |  | Week-24 |  |  |  |  | Week-25 |  |  |  |  | Week-26 |  |  |  |  | Week-27 |  |  |  |  | Week-28
Work Tasks | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 5
1.1.1 Planning
1.1.2 Cost & Schedule Management
1.1.3 Scope Management
1.1.4 Task Management
1.1.5 Project Communication
1.1.6 Risk Management
1.1.7 Quality Management
Milestone : Project Management Defined
1.2.1 Technical plannning
1.2.2 Technical supervision
1.2.3 Business requirement definition
1.2.4 System Architecture & Top-level design
Milestone : System Engineering Complete
1.3.1.1 Software Requirement Specification
1.3.1.2 Software Prototyping
1.3.1.3 Software unit detailed design
Goal : Software Design Complete
1.3.2.1 Software unit coding
1.3.2.2 Software unit debugging
Milestone : Software Build Complete
1.3.3.1 Unit testing planning
1.3.3.2 Unit test case preparation
1.3.3.3 Unit testing conduct
1.3.3.4 Unit test records
Milestone : Unit Testing Complete
1.4.1 Deliverables tracking
Milestone : Deliverables Management Defined
1.5.1 User feedback
1.5.2 Development tools and utilities
1.5.3 Team technical training
1.5.4 User training session
1.5.5 Configuration management
Milestone : Support services Defined
1.6.1 Module & Subsystem Testing
1.6.2 System integration Testing
1.6.3 Acceptance Testing
1.6.4 Defect Tracking
Milestone : System Testing Complete
1.7.1 Installation Planning
1.7.2 User Support documentation
1.7.3 User communication & traning
1.7.4 Installation management
1.7.5 Installation testing and verification
1.7.6 Installation performance monitoring
Milestone : Installation Complete